## Slide 1: Progress Meeting 03/04/2020
Notes: Useful books for creating MATLAB solver:
Fundamentals of engineering numerical analysis – Parvis Moin
Stability and transition in shear flows – Peter Schmid

## Slide 2
Chart: 
| MATLAB Solver: pCf/pPf Orr-Sommerfeld | MATLAB Solver: pCf/pPf Orr-Sommerfeld | Solver validation | Solver validation | Derive Orr-Sommerfeld system with stratification | Derive Orr-Sommerfeld system with stratification | MATLAB Solver: pCf/pPf Orr-Sommerfeld with stratification | MATLAB Solver: pCf/pPf Orr-Sommerfeld with stratification | Investigate flow stability with stratification inalignment | Investigate flow stability with stratification inalignment | Introduction to non-linear stability | Introduction to non-linear stability | THESIS | THESIS
Start Date | 43916 | 43916 | 43916 | 43916 | 43920 | 43922 | 43927 | 43941 | 43954 | 43921 | 43919
Duratioj | 4 | 4 | 5 | 6 | 7 | 2 | 14 | 0 | 13 | 0 | 18 | 0 | 62 | 5

## Slide 3: Progress
Went through code
  Fully debugged the code
  Now matches the Appendix of Schmid and Henningson
  Matches results from literature (Re = 10000)
  Code gives critical Re for plane Poiseuille flow at 5772 -> Correct!

## Slide 4: Questions about the code
Plotting U vector does not give a straight line for pCf?
Chebyshev grid points appear not to be cosine mesh?
Am I interested in the Squire system?
  Instabilities come from Orr-Somm?

## Slide 5: Working On…
Deriving the Orr-Sommerfeld Eigenvalue Problem with the stratified shear flows with the inalignment
  Went through Hydrodynamic Stability lecture notes derivation
  Determining governing equations for stratified shear flow

## Slide 6: Coordinate System

## Slide 7: Governing Equation

## Slide 8: Questions on derivation
The rho in the governing equation – is that a density perturbation or the density profile: rho(Z)?
Am I employing linear density gradient?
Do I need to non-dimensionalise the governing equations?
Where does Froude number come into the equations?

## Slide 9: Plan for next week
Finish deriving stratified shear flow eigenvalue system
  Linearise governing equations
  Follow Orr-Somm derivation
Start implementing it into the MATLAB Solver